## Features
Project: hailua.com.vn | Music Player
Team: 5 | 1
ID | Feature Name | Description | Remark
UC01 | Searching | Search by criteria: by song's name, artist
UC02 | Create/Remove playlist | Create/Remove personal playlist
UC03 | Music function button | Play/Pause, Shuffle, Repeat, Backward, Forward button and SeekBar when listening to music

## Test cases
Function/Feature ID | Case ID | Test case name | Test step | Expected Result (ER) | Actual Result | Status | Tester | Tested Date | Remark
Function 01:Searching
UC01 | UI01 | Search for song by name | 1. Choose "by Song" in filter button (default) 2. Enter text | 1. 10 songs that have search keyword in their name will be displayed | The same as ER | Pass | Minh Phúc | 2022-10-08
UC01 | UI02 | Search for song by artist | 1. Choose "by Artist" in filter button 2. Enter text | 1. 10 songs that have search keyword in their artist's name will be displayed | Result shows songs that match by name | Failed | Minh Phúc | 2022-10-08
UC01 | UI03 | Search for song by any criteria but with blank input | 1. Choose any option in filter button 2. Enter text "" | 1. 10 random songs will be displayed in alphabetical order | The same as ER | Pass | Minh Phúc | 2022-10-08
UC01 | UI04 | Search for song that doesn't have in database | 1. Choose any option in filter button 2. Enter text | 1. None songs will be displayed | The same as ER | Pass | Minh Phúc | 2022-10-08
Function 02: Create/Remove playlist
UC02 | UI01 | Create valid playlist | 1. Click + button 2. Enter playlist name 3. Click OK | 1. The success message should be displayed 2. New playlist will be displayed | The same as ER | Pass | Samuel | 2022-10-08
UC02 | UI02 | Create playlist with the same name as other | 1. Click + button 2. Enter an existed playlist name 3. Click OK | 1. The success message should be displayed 2. New playlist will be displayed | The same as ER | Pass | Samuel | 2022-10-08
UC02 | UI03 | Create playlist with blank name | 1. Click + button 2. Click OK | 1. Disallows the user to enter blank name 2. The warning message should be displayed | If playlist has been created before, new playlist with the same name will be created | Failed | Samuel | 2022-10-08
UC02 | UI04 | Remove a playlist but agree | 1. Click - button 2. Click Yes on warning | 1. Allow the user to remove playlist 2. A successful message will be displayed | The same as ER | Pass | Samuel | 2022-10-08
UC02 | UI05 | Remove a playlist but refuse | 1. Click - button 2. Click No on warning | 1. Allow the user to cancel ther removal | The same as ER | Pass | Samuel | 2022-10-08
Function 03: Music function button
UC03 | UI01 | Play/Pause button | 1. If song is played, click Pause button 2. If song is pause, click Play button | 1. If Pause button is clicked, song will be paused 2. If Play button is clicked, song will be played | The same as ER | Pass | Anh Thư | 2022-11-08
UC03 | UI02 | Backward button | 1. Click Backward button | 1. The previous song in playlist will be played | The same as ER | Pass | Anh Thư | 2022-11-08
UC03 | UI03 | Forward button | 1. Click Fordward button | 1. The next song in playlist will be played | The same as ER | Pass | Anh Thư | 2022-11-08
UC03 | UI04 | Default Repeat button | 1. Wait for the last song in playlist to be finished | 1. No song will be played next | The same as ER | Pass | Thiện Tiến | 2022-11-08
UC03 | UI05 | Repeat button is clicked once from default | 1. Click repeat button once 2. Wait for the last song in playlist to be finished | 1. The first song of playlist will be played next | The same as ER | Pass | Thiện Tiến | 2022-11-08
UC03 | UI06 | Repeat button is clicked twice from default | 1. Click Repeat button twice 2. Wait for a song to be finished | 1. The current song will be looped | The same as ER | Pass | Thiện Tiến | 2022-11-08
UC03 | UI07 | Default Shuffle button | 1. Wait for a song to be finished | 1. Songs in playlist will be play in alphabetical order 2. Next song with name come after the current song in playlist will be played | The same as ER | Pass | Thiện Tiến | 2022-11-08
UC03 | UI08 | Shuffle button is clicked once | 1. Click Shuffle button once 2. Wait for a song to be finished | 1. Songs in playlist will be play in random order 2. Next random song in playlist will be played | The same as ER | Pass | Thiện Tiến | 2022-11-08
UC03 | UI09 | Moving SeekBar | 1. Drag the SeekBar to any position | 1. Current song will be played from that position | After dragging seekbar, Play/Pause button may be incorrect | Failed | Thiện Tiến | 2022-11-08